CQC Improvement Plan Template

A free, fillable improvement (action) plan with evidence tracking, by CQCLogic. cqclogic.co.uk

Service: ______________________________   Registered manager: ______________________________   Date started: ______________

How to use it

1. Add one row per finding, regulation breach or concern, from your CQC report or your own audits. Delete the grey example row when you start.

2. Fill every shaded cell. The evidence columns matter most at reinspection: what an inspector would need to see to believe the action is done.

3. Update Status as you go: Not started, In progress, Complete - not yet evidenced, or Complete - evidenced. Only use "Complete - evidenced" once the evidence is collected and verified. Inspectors treat "complete" without evidence as "not done".

4. Log every piece of evidence in section 2, using the same Ref as the action it supports.

5. Run a mock inspection 4 to 6 weeks before an expected reinspection, and record the gaps in section 3. Treat each gap like a real finding, with an owner and a deadline.

Guidance: what to include and why  |  how to write the full plan

1. Improvement plan

| Ref | Key question | Finding / regulation cited | Action required | Named owner | Deadline | Evidence required | Evidence collected? (Y/N) | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EX | Safe | Reg 12: medicines given without a second-person check on 3 of 8 MARs sampled | Introduce second-person check on all controlled drugs; retrain 14 staff; weekly MAR audit for 8 weeks | J. Smith (Registered Manager) | 31/10/2026 | Signed training records; 8 weekly audit sheets showing a falling error rate | N | In progress |

2. Evidence log

One row per piece of evidence, using the same Ref as the action it proves. Inspectors want dated, verified evidence, not a folder of unlabelled files.

| Action Ref | Evidence item | Date collected | Collected by | Verified by | Where it is kept (folder / link) |
| --- | --- | --- | --- | --- | --- |
| EX | Weekly MAR audit, week 3 (14 units checked, 1 error) | 10/10/2026 | A. Patel | J. Smith | Shared drive > Evidence > Safe > Medicines |

3. Mock inspection log

Test against your actual improvement plan and interview staff directly. Add every gap to the plan above.

| Date | Key question | What was tested | Gap found | Action Ref | Owner | Deadline |
| --- | --- | --- | --- | --- | --- | --- |
| 05/11/2026 | Well-led | Asked 3 staff to explain the new medicines check | 2 of 3 could not describe the second-person check | A12 | J. Smith | 12/11/2026 |

Want it built for you? CQCLogic builds a structured improvement plan from your actual CQC inspection data within 24 hours, with every action linked to a concern, a regulation and the evidence to collect. See a sample: cqclogic.co.uk/sample-plan

This template is a working tool, not legal advice or an official CQC form. CQC does not require a specific format for an improvement plan.